## Precon Activities Matrix
OP-020.1 Preconstruction Activities Matrix
# | Preconstruction Activities | Program Estimate | ConceptualEstimate | SD Estimate | DD Estimate | 50-100% Estimate | Final Estimate
1 | Research historical cost database for similar projects | x | x | x
2 | Develop average costs for similar projects | x | x | x
3 | Adjust average or historical costs for area or region of proposed project | x | x | x
4 | Escalate costs to adjust for proposed project start date | x | x | x | x
5 | Research local business, labor & sub market noting potential risks | x | x | x | x | x | x
6 | Review proposed site conditions if site is known | x | x | x | x | x | x
7 | Determine required preconstruction staffing and responsibilities | x | x | x | x | x | x
8 | Determine required on-site staffing for construction | x | x | x | x | x | x
9 | Self performed work strategy meeting | x | x | x | x | x | x
10 | Determine strategy to price & build the project |  | x | x | x | x | x
11 | Produce an overall project schedule | x | x | x | x | x | x
12 | Produce a site utilization & logistics plan if site is known | x | x | x | x | x | x
13 | Identify potential work to self perform |  | x | x | x | x | x
14 | Evaluate prefabrication / modular construction opportunities |  |  | x | x | x | x
15 | Find out if Owner desires sub/vendor input | x | x
16 | Create a General Conditions estimate | x | x | x | x | x | x
17 | Determine quantities by performing a quantity survey |  | x | x | x | x | x
18 | Determine level of and obtain sub/vendor pricing input |  | x | x | x | x | x
19 | Solicit local and national subs/vendors to organize list of qualified bidders |  |  | x | x | x | x
20 | Scope sub/vendor pricing |  |  | x | x | x | x
21 | Obtain BIM if available | x | x | x | x | x | x
22 | Create estimate | x | x | x | x | x | x
23 | Create & document assumptions or Proposal Qualifications | x | x | x | x | x | x
24 | Completely audit the estimate | x | x | x | x | x | x
25 | Create estimate presentation materials | x | x | x | x | x | x
26 | Present the estimate | x | x | x | x | x | x
27 | Attend preconstruction team meetings and focus on leading the meeting |  |  | x | x | x | x
28 | Review specific contract terms if contract is available | x | x | x | x | x | x
29 | Include profit enhancement per the contract or per policies |  |  | x | x | x | x
30 | Include all R&M OH costs that are required for each project | x | x | x | x | x | x
31 | Provide cost management suggestions |  |  | x | x | x | x
32 | Hold regular in-house meetings to review project status, risks, etc. |  |  | x | x | x | x
33 | Understand Project Delivery Method and potential costs associated (IPD, etc.) | x | x | x | x | x | x
34 | Provide comparison to previous estimates |  |  | x | x | x | x
35 | Contingency plan | x | x | x | x | x | x