## Form OP-030.2
Project Name
OP-030.2 -- Preconstruction Estimate Action List | [5 empty] | 2024-07-24
Item | Policy | Description | Resp | Target Date | Completed | Notes/Comments
1.00 - General:
1.01 | OP-010 | Set-Up Estimate Number & General Files
1.02 | OP-030 | Project Kick-off Meeting with Project Team
1.03 |  | Confirm Precon Team
1.04 |  | Identify Key Field Operations Personnel
1.05 |  | General Project Overview
1.06 |  | Request Access to Model files
1.07 |  | Inventory Documents |  |  |  | Estimate Folder (req'd), Others: ProCore, Bldg Connected, etc.
1.08 |  | Establish/Identify Milestone Dates
1.09 | OP-100 | Jobsite Visit Checklist
2.00 - Building Forward Plan:
2.01 |  | Identify Champion or Advocate to assist
2.02 |  | Conditions of Satisfaction
2.03 |  | Integrated Precon Approach |  |  |  | Estimate Approach/TVD, PIT Meetings, Prefab/Modular Opportunities, etc.
2.04 |  | Onboarding / Alignment Plan
2.05 |  | Set-up Procore Project |  |  |  | Team Directory and Document Distribution
2.06 |  | CoLo Plan / Establish Team Call, Day & Time
2.07 |  | Documentation Plan |  |  |  | WWP, Action Items, Record Keeper
3.00 - Services & Strategies:
3.01 | OP-090 | Funding of R&M Internal Services:
3.01a | OP-090.1 | Safety
3.01b | OP-090.2 | Preconstruction
3.01c | OP-090.3 | BIM/VDC Costs
3.01d | OP-090.4 | Scheduling
3.01e | OP-090.5 | Moisture Control
3.01f | OP-090.6 | Jobsite IT Services
3.01g | OP-090.7 | JET Services
3.01H | OP-090.8 | Building Forward Services
3.02 | OP-180 | Fee / Profit Strategy or Contract Terms:
3.02a |  | Review Owner Contract for Terms
3.02b |  | Base Fee
3.03 |  | Self-Perform Work:
3.03a |  | Concrete
3.03b |  | General Requirements
3.03c |  | Masonry
3.03d |  | General Trades
3.03e |  | Doors/Hardware
3.03f |  | Drywall
3.03g |  | Acoustical
3.03h |  | Low Voltage
3.04 |  | Labor Burden Rates:
3.04a |  | Salaried Personnel
3.04b |  | Hourly Personnel
3.04c |  | Raises (How to Fund)
3.05 |  | Risk Management:
3.05a |  | Builder's Risk
3.05b |  | BR Difference in Coverage
3.05c |  | Contract Insurance
3.05d |  | R&M P&P Bond Required?
3.05e |  | Subcontractor P&P Bonds
3.05f |  | Sub Default Insurance
3.06 |  | ERS Utilization
3.07 |  | Miscellaneous:
3.07a |  | Textura Cost
3.07b |  | Procore Cost
3.07c |  | Unbillable cost
3.07d |  | R&M Technology / IT Fee
3.07e |  | PPE %, Small Tools %
3.07f |  | Contractor Owned Equipment Terms
3.07g |  | Warranty Escrow Terms
3.08 |  | Contract Duration Verification
3.09 |  | Smart-Fab
3.1 |  | Pre-Fab Opportunities & Initiatives
3.11 |  | BIM/VDC Services - Scope & Approach
3.12 |  | Scheduling (Internal vs. Consultant)
3.13 | OM-475 | Building Envelope / Moisture Control
3.14 |  | Project Specific Marketing Plan: |  |  |  | Include Marketing team rep to help formulate marketing plan
3.14a |  | Jobsite Signage |  |  |  | Please review all in-stock signage and windscreen options: https://ersstore.com/collections/signage-2
3.14b |  | R&M Branded ICRA/Edgeguard Panels |  |  |  | If purchasing ICRA panels, please consider branded or co-branded panels for your project. Please contact your marketing team member and/or ERS sales representative for additional cost information and branding options.
3.14c |  | Windscreen |  |  |  | Please contact your marketing team member for any custom signage/windscreen needs
3.14d |  | Final Project Photography cost |  |  |  | • Small, interior renovations: up to $5,000 • Large scale projects: up to $10,000
3.15 |  | Technology Strategy:
3.15a | OIT-010.1 | Information Technology Equipment Procurement
3.15b | OIT-010.2 | Jobsite IT Setup and Jobsite Engagement Team (JET)
3.16 | OP-170 | Discuss Prequalification Process/Timeline
3.17 | OS-240 | Develop ICRA Plan
3.18 |  | Third-Party Consultants:
3.18a | OS-240 | ICRA Consultant
3.18b | OM-530 | ADA Reviews / Consultant
3.18c |  | Misc. Third-Party Consultants:
4.00 - Operations & Special Conditions:
4.01 |  | Safety Plan
4.02 | OP-110 | Site Utilization & Logistics Plan
4.03 |  | Site Conditions / Issues
4.04 |  | Constructability Issues / Review
4.05 |  | Weather Conditions & Potential Impacts
4.06 | OP-050 | Preconstruction Phase Schedule
4.07 |  | BIM Execution Plan
4.08 |  | Building Forward Plan
4.09 |  | Jobsite Rules
4.1 |  | Layout Strategy & Funding |  |  |  | How is layout being funded? (If SPW is included in project -- e.g. coordinate layout cost responsibility between main estimate and self perform estimates, etc.)
5.00 - Subcontractors & Vendors:
5.01 | OP-120 | Assemble Bid List & Issue Invitations |  |  |  | Building Connected
5.02 | OP-170 | Prequalification Process |  |  |  | Issue form (Exhibit C), establish due date. Review and approval process
5.03 | OP-130 | Invitation to Bid
5.04 | OP-130.1 | Interested Bidders Memo:
5.04a | OS-041 | Exhibit A1: Subcontract
5.04b | OS-044 | Exhibit A2: R&M Purchase Order
5.04c |  | Exhibit B: Redacted Owner Contract
5.04d | OP-170.1 | Exhibit C: Trade Partner Qualification Form
5.04e |  | Exhibit D: Building Forward Plan
5.04f | OP-050 | Exhibit E: CD Schedule
5.04g | OP-110 | Exhibit F: Site Utilization & Logistics Plan
5.04h | OP-130.2 | Exhibit G: Jobsite Rules and Regulations Bulletin
5.05 |  | Other possible pertinent documents:
5.05a |  | Bid Package Listing
5.05b |  | Bid Packages and Proposal Forms |  |  |  | Reference Precon Lean Library for Bid Package examples, if used
5.05c |  | BIM/VDC Implementation Plan
5.05d | OP-140 | Sustainability/LEED Implementation Plan
5.05e |  | Geotechnical Reports
5.05f |  | Statement of Special Inspections
5.05g |  | Project Wage Determinations
5.05h |  | Infection Control / Interim LS Measures
5.05i |  | Project Specific Truck/Delivery Maps
5.05j |  | Crane load tables/information
5.05k |  | RFI Log
5.05l |  | Caulking / Firestopping Matrix
5.05m |  | CCIP / OCIP Manual
5.05n |  | 3PL Plan (3rd Party Logistics)
5.05o |  | SmartFab Plan
5.05p |  | Prefabrication Plan
5.05q |  | QaS Program (Quality at the Source)
5.05r |  | Safety Plan
5.06 |  | Owner Supplemental Requirements |  |  |  | Confirm where Prevailing Wages, HUB plan, MWBE plan, etc. communicated
5.07 |  | Pre-Bid Meeting(s) |  |  |  | In-Person/On-Site or Virtual/Video Presentation
5.08 |  | Telephone Follow-Up with Subs
5.09 |  | RFIs & Plan Review Comments
5.1 | OP-190.2 | Bid Analysis Sheets
5.11 |  | Receive Bids
5.12 | OP-160 | Receive Bid Bonds
6.00 - Estimate Development:
6.02 |  | General Conditions & Project Overhead
6.02a | AA-065 | High Cost City Living Allowance Adjustment Required?
6.05 |  | Consultant Costs:
6.05a |  | ADA Consultant
6.05b |  | Moisture Consultant
6.05c |  | LEED
6.05d |  | Commissioning
6.05e |  | Materials & Testing
6.05f |  | ICRA
6.05g |  | Scheduling
6.06 |  | Logistics & Schedule Costs:
6.06a |  | Off Site Parking
6.06b |  | Work in Occupied Space
6.06c |  | Night Work Premium
6.07 |  | Utility Services:
6.07a |  | Temp Utility Usage
6.07b |  | Utility Consumption Charges
6.08 |  | AHJ / Inspections:
6.08a |  | State Inspection Costs
6.08b |  | AHCA Coordination
6.09 |  | Testing Fees:
6.09a |  | Testing & Inspection Fee
6.09b |  | Threshold Inspection Fee
6.1 |  | Permits & Taxes:
6.10a |  | Building Permit Cost
6.10b |  | Plan Check Fee
6.10c |  | Permit Expediter
6.10d |  | Subcontractor Permit Fees
6.10e |  | Impact Fees
6.10f |  | Business License Fees |  |  |  | for both R&M and Trade Partners
6.10g |  | Gross Receipts Taxes
6.10h |  | Renovation Taxes
6.11 |  | Misc. Cost Items:
6.11a |  | Liquidated Damage Fees
6.11b |  | Legal Fees
6.11c |  | AL Workforce Development Fee
6.11d |  | Third Party Fees
6.12 |  | Technology:
6.12a |  | R&M Technology / IT Fee
6.12b |  | Procore Set Up Fee
6.12c |  | Textura Set Up Fee
6.12d |  | Textura Subcontractor Fees
6.13 |  | Insurance:
6.13a |  | General Liability
6.13b |  | Builders Risk
6.13c |  | BR Difference in Coverage Fee/Terms
6.13d |  | OCIP / CCIP
6.13e |  | Subcontract Bonds / SDI Terms
6.13f |  | For SPW Packages, how are SDI/Bonds' cost carried?
6.13g |  | R&M P&P Bond
6.14 |  | Contingency:
6.14a |  | Design Contingency
6.14b |  | Estimating Contingency
6.14c |  | Construction Contingency
6.14c |  | Escalation
6.15 |  | Fee
6.16 |  | Quantity Take-off
6.17 |  | Div. 01 General Conditions
6.18 |  | Div. 02 Sitework & Grading
6.19 |  | Div. 02 Paving & Site Concrete
6.2 |  | Div. 02 Site Utilities
6.21 |  | Div. 02 Landscaping & Irrigation
6.22 |  | Div. 02 Shoring
6.23 |  | Div. 02 Deep Foundations
6.24 |  | Div. 02 Miscellaneous
6.25 |  | Div. 03 Concrete
6.26 |  | Div. 03 Precast
6.27 |  | Div. 03 Hoisting
6.28 |  | Div. 04 Masonry
6.29 |  | Div. 05 Structural Steel
6.3 |  | Div. 05 Ornamental Metals
6.31 |  | Div. 06 Rough Carpentry
6.32 |  | Div. 06 Finish Carpentry / Millwork
6.33 |  | Div. 07 Roofing
6.34 |  | Div. 07 Waterproofing
6.35 |  | Div. 07 Fireproofing
6.36 |  | Div. 07 Firestopping
6.37 |  | Div. 07 EIFS
6.38 |  | Div. 07 Metal Wall Panels
6.39 |  | Div. 08 Doors, Frames & Hardware
6.4 |  | Div. 08 Glass & Glazing
6.41 |  | Div. 09 Drywall & Ceilings
6.42 |  | Div. 09 Flooring & Tile
6.43 |  | Div. 09 Painting & Wall Covering
6.44 |  | Div. 09 Stucco
6.45 |  | Div. 10 Specialties
6.46 |  | Div. 11 Appliances & Equipment
6.47 |  | Div. 12 Casework
6.48 |  | Div. 12 Furnishings
6.49 |  | Div. 13 Special Construction
6.5 |  | Div. 14 Pneumatic Tube Systems
6.51 |  | Div. 14 Elevators
6.52 |  | Div. 15 Mechanical & Plumbing
6.53 |  | Div. 15 Fire Protection
6.54 |  | Div. 16 Electrical
6.55 |  | Div. 17 Low Voltage Systems
6.56 |  | Estimate Assembly & Pricing
6.57 |  | Check & Audit Estimate
6.58 |  | Preliminary Review with R&M Team
7.00 - Estimate Presentation:
7.01 | OP-200 | Estimate Presentation:
7.01a |  | Cover Page
7.01b |  | Cover Letter
7.01c | OP-210 | Estimate Summary
7.01d |  | Bidders Recap
7.01e |  | Proposal Qualifications
7.01f |  | Alternates Listing
7.01g |  | Cost Management Suggestions
7.01h |  | Allowance Summary
7.01i |  | Unit Price Summary
7.01j | OP-050 | CD Estimate Schedule
7.02 |  | Assemble Presentation Books/Files
7.03 |  | Preview Est. Pres. with Owner's Rep / Design Team
7.04 |  | Present to Owner
7.05 | OP-220 | Cash Flow Projection
7.06 |  | Compile hand-off books/files for Operations |  |  |  | Copies of quotes, scope sheets, cost mngt, etc.
8.00 - Miscellaneous:
8.01 |  | Identify Opportunities for Failures
8.02 |  | Identify R&M Advantages / Strengths
8.03 |  | Labor Availability/Sources
8.04 |  | Economic Conditions
9.00 - Final Transfer / Hand-Off:
9.01 | OP-250 | Transfer Estimate to Accounting
9.02 | OP-260 | Publish Project to Historical Database
9.03 | OS-050 | Hand-Off to Operations / Project Kick-Off Meeting